## Project Plan
Color Coding |  | Completed |  |  |  | FALL 2022 SEMESTER
In Progress
[5 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[5 empty] | Date | 2022-09-13 | 2022-09-20 | 2022-09-27 | 2022-10-04 | 2022-10-11 | 2022-10-18 | 2022-10-25 | 2022-11-01 | 2022-11-08 | 2022-11-15 | 2022-11-22 | 2022-11-29 | 2022-12-06 | 2022-12-13 | 2022-12-20
Project Phase | Activity | Task Owner Name | Start Date | End Date | Progress %
Project Planning | Project Proposals - Business Cases (2) | Tarun Dagar | 2022-09-13 | 2022-09-18 | 100%
| Project Initiation Document (PID), initial draft | Tarun Dagar | 2022-09-13 | 2022-09-30 | 100%
| RACI Table | Aliaksandra Paliashchuk | 2022-09-20 | 2022-10-11 | 100%
| Completed PID | Tarun Dagar | 2022-09-20 | 2022-09-30 | 100%
| Start developing Home Page | Fernando Hernandez | 2022-09-27 | 2022-10-11 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Analysis | BRM Diagram, User Roles | Riddhi Mhatre | 2022-10-11 | 2022-10-16 | 100%
| Context Diagram, System Interface Table | Vivek Karhale | 2022-10-11 | 2022-10-16 | 100%
| Team discussion of Requirements Types | Tarun Dagar | 2022-10-11 | 2022-10-16 | 100%
| Compile a list of Customer needs | Riddhi Mhatre | 2022-10-11 | 2022-10-16 | 100%
| Business Requirements | Riddhi Mhatre | 2022-10-18 | 2022-10-23 | 100%
| Functional Decomposition (assign SME), Fishbone Diagram | Vivek Karhale | 2022-10-18 | 2022-10-23 | 100%
| RCT (includes supplementary requirements) | Vivek Karhale | 2022-10-18 | 2022-10-23 | 100%
| Home Page menu structure | Fernando Hernandez | 2022-10-18 | 2022-10-23 | 100%
| Select in the RCT a few features to implement this semester, including crosscuts. | Riddhi Mhatre | 2022-10-25 | 2022-10-30 | 100%
| UML analysis diagrams (use case, activity diagrams) | Vivek Karhale | 2022-10-25 | 2022-10-30 | 100%
| Data-flow Diagram (logical) | Vivek Karhale | 2022-10-25 | 2022-10-30 | 100%
| Functional Requirements (user stories) | Vivek Karhale | 2022-10-25 | 2022-10-30 | 100%
| Complete Home Page Demo | Sriharsha Mopidevi, Fernando Hernandez | 2022-10-25 | 2022-10-30 | 100%
| Project Plan: Elaborate the Coding/Testing phases with the selected features | Tarun Dagar | 2022-10-25 | 2022-10-30 | 100%
| Requirements Workshop (WS1): preparation | All | 2018-03-06 | 2022-11-01 | 0%
MILESTONE 2: REQUIREMENTS COMPLETED
High-level Design | ER Diagrams (conceptual -> logical), identify reference tables | Jigarkumar R Patel | 2022-11-01 | 2022-11-13 | 100%
| Database Table Specification | Jigarkumar R Patel | 2022-11-01 | 2022-11-13 | 100%
| Reference Data Specification | Jigarkumar R Patel | 2022-11-01 | 2022-11-13 | 100%
| Data-flow Diagram (physical) | Vivek Karhale | 2022-11-01 | 2022-11-13 | 100%
| Architecture Diagrams (2) | Sriharsha Mopidevi/Jigarkumar R Patel | 2022-11-15 | 2022-11-20 | 100%
| Establish GitHub projects; Watch Git tutorial on YouTube | All | 2022-11-15 | 2022-11-20 | 100%
MILESTONE 3: DESIGN COMPLETED
Implementation | Class Diagram (UML) | Fernando Hernandez | 2022-11-22 | 2022-11-27 | 100%
| Sequence Diagram (UML) | Sriharsha Mopidevi | 2022-11-22 | 2022-11-27 | 100%
| Development (Web / Mobile Application) | Shriharsha Mopidevi, Fernando Hernandez | 2022-11-22 | 2022-11-27 | 100%
| Populate reference (static) data in the database tables | Jigarkumar R Patel | 2022-11-22 | 2022-11-27 | 100%
| Source code in GitHub repository, executable code ready for testing | Shriharsha Mopidevi, Fernando Hernandez | 2022-11-22 | 2022-11-27 | 100%
| UI/UX Design - Fall 2022 Features | Riddhi Mhatre, Vivek Karhale | 2022-11-15 | 2022-11-27 | 100%
| Software Architecture Design | Tarun Dagar | 2022-11-15 | 2022-11-27 | 100%
| Software Architecture Setup | Sriharsha Mopidevi | 2022-11-15 | 2022-11-27 | 100%
| Database Design & Setup | Jigarkumar R Patel | 2022-11-15 | 2022-11-27 | 100%
| Feature Implementation - Authenticate Account - GUI | Sriharsha Mopidevi | 2022-11-15 | 2022-11-27 | 100%
| Feature Implementation - Authenticate Account - Core | Fernando Hernandez | 2022-11-15 | 2022-11-27 | 100%
| Feature Implementation - Access/View Account Summary - GUI | Sriharsha Mopidevi | 2022-11-15 | 2022-11-27 | 100%
| Feature Implementation - Access/View Account Summary - Core | Fernando Hernandez | 2022-11-15 | 2022-11-27 | 100%
| Feature Implementation - Authenticate Account - Field Validation | Sriharsha Mopidevi | 2022-11-15 | 2022-11-27 | 100%
| Feature Implementation - Authenticate Account - Logging | Fernando Hernandez | 2022-11-15 | 2022-11-27 | 100%
| Feature Implementation - Authenticate Account - Performance | Fernando Hernandez | 2022-11-15 | 2022-11-27 | 100%
| Feature Implementation - Access/View Account Summary - Field Validation | Sriharsha Mopidevi | 2022-11-15 | 2022-11-27 | 100%
| Feature Implementation - Access/View Account Summary - Logging | Fernando Hernandez | 2022-11-15 | 2022-11-27 | 100%
| Feature Implementation - Access/View Account Summary - Performance | Fernando Hernandez | 2022-11-15 | 2022-11-27 | 100%
| Dev/QA environment setup | Shriharsha Mopidevi, Fernando Hernandez | 2022-11-15 | 2022-11-27 | 0%
| Deployment | Shriharsha Mopidevi, Fernando Hernandez | 2022-11-15 | 2022-11-27 | 75%
MILESTONE 4: CODING COMPLETED
| Produce Test plan document | Aliaksandra Paliashchuk, Nishith Desai | 2022-11-22 | 2022-11-29 | 100%
| Create Test design, test cases (in Excel template) - 1.01 Authenticate Account | Aliaksandra Paliashchuk, Nishith Desai | 2022-11-22 | 2022-11-29 | 100%
| Create Test design, test cases (in Excel template) - 1.02 Access/View Account Summary | Aliaksandra Paliashchuk, Nishith Desai | 2022-11-22 | 2022-11-29 | 100%
| Test Execution - 1.01 Authenticate Account | Aliaksandra Paliashchuk, Nishith Desai | 2022-11-29 | 2022-12-04 | 100%
| Test Execution - 1.02 Access/View Account Summary | Aliaksandra Paliashchuk, Nishith Desai | 2022-11-29 | 2022-12-04 | 100%
| Bug Fixes - 1.01 Authenticate Account | Aliaksandra Paliashchuk, Nishith Desai | 2022-11-29 | 2022-12-04 | 100%
| Bug Fixes - 1.02 Access/View Account Summary | Aliaksandra Paliashchuk, Nishith Desai | 2022-11-29 | 2022-12-04 | 100%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation | ALL | 2022-12-13 | 2022-12-20 | 100%

## RACI
Responsible, Accountable, Consulted, Informed |  | Project Roles
Process Area | Project Tasks | Project Manager | Product Owner | Dev Lead | BA Lead | QA Lead | Tester | DBA
Project Management | Develop a project plan | A,R | C | C | C | C | C | I
| Provide cost estimate | A,R | C | C | C | C | I | I
| Hire resources | A,R | C | C | C | C | I | I
| Establish a project portal on SharePoint | A,R | R | I | I | I | I | I
| Maintain a project risk and issue log | A,R | R | C | C | C | C | I
| Provide project status reports | A,R | R | C | C | C | C | C
Requirements | Perform requirements analysts | A | R | R | R | I | I | R
| Gather business requirements | R | A | C | R | I | I | I
| Produce functional requirements | A | I | C | R | C | I | I
Design | Produce high-level design specs | A | I | R | C | I | I | C
| Produce data model | A | I | C | C | I | I | R
| Produce detailed design specs | A | I | R | C | I | I | R
Coding | Establish a code repository | A | I | R | I | I | I | C
| Develop component code | A | I | R | I | I | I | C
Testing | Develop a test plan | A | I | C | C | R | C | C
| Establish a test repository | A | I | C | I | R | C | I
| Develop test specifications | A | I | C | I | R | R | I
| Execute testing, report defects | A | I | I | I | R | R | I
| Conduct defect review calls | A | I | C | R | R | R | C
| Produce, deliver defect metrics | A | I | C | R | R | R | I
| Support test environments | A | I | R | C | C | I | R
Deployment | Produce a deployment plan | A | C | R | I | I | I | R
| Produce deployment procedures | A | I | R | I | I | I | R
| Deploy software into production | A | I | R | C | C | C | R